## Sheet1
INEQE AUDIT 2025 DIOCESE OF DURHAM: DBF RECOMMENDATIONS Appendix 1 | Real time Action | Impact | Status | National Safeguarding Standard (s) | Owner | Timescale to implement | Additional Comments | Updates
Recommendation D1: To enhance support for the Diocesan Bishop and ensure continuous senior leadership oversight of safeguarding matters, it is recommended that a Suffragan Bishop be formally integrated into the DBF safeguarding processes. The responsibilities of the Suffragan Bishop should include maintaining awareness of safeguarding matters, attending relevant safeguarding meetings, supporting the Diocesan Bishop on safeguarding issues, and providing objective perspectives and challenge on complex issues. For effective implementation, the role requires a clear definition that maintains the Diocesan Bishop's ultimate accountability. | Include Suffrrgan Bishop in regular meetings between new BIshop and DSO | Suffragan Bishop maintains awareness of safeguarding matters and is able to inform discussions. | Not yet started | Culture, Leadership & Capacity | Bishop / DSO | 2026-06-01 | Implementation once new Diocesan Bishop Has been appointed and is in post.
Recommendation D2: To optimise strategic oversight and information sharing without diluting the safeguarding responsibilities of all Archdeacons, the Audit recommends the role of 'Lead Archdeacon’. This could help to create a clearer point of contact, potentially through a rotating responsibility that broadens understanding and ensures consistent attendance (from at least one Archdeacon) at all Safeguarding Management Group (SMG) meetings. | All Archdeacons including Lead Archdeacon for Safeguarding to attend future SMG meetings | All Archdeacons fully engaged with safeguarding matters and fully informed of issues and developments. | In Progress | Culture, Leadership & Capacity | Lead Archdeacon for Safeguarding | 2026-06-01 | Full implementation once Diocesan Bishop appointed. | From September 2025 all three Archdeacons are members of Safeguarding Management Group.
Recommendation D3: To ensure Archdeacons are comprehensively informed and effective during parish engagements (including informal visits and more formal visitations / inspections), the DBF should enhance the existing process and templates for all pre planned parish visits. This should include implementing annual planning meetings with the Diocesan Safeguarding Team (DST) to align strategies. Crucially, pre-visit briefings from the Diocesan Safeguarding Officer (DSO) should also be formalised, providing Archdeacons with updates about all relevant safeguarding issues, specific cases, and the status of any safety plans pertinent to their geographical area. This will allow for Archdeacons to be fully sighted on concerns and more equipped to test and support good safeguarding practice. Following visits, post-visit debriefings with the DSO and DST are recommended to capture insights and inform diocesan strategy. In addition, to assure itself of the quality and impact of Parish Dashboard data, the DBF should define and adopt a Parish Dashboard quality assurance process. While it should be built on the principle of ‘working with’ rather than ‘doing to’, this process should involve dip sampling to test the veracity of Parish Dashboard data. | 1 - Review templates, processes and information obtained form parishes prior to inspections 2 - Standing agenda item on SMG agenda -Action around informal visits, each Archdeacon informs SMG of any issues noted whilst visiting parishes recommendations and practices. 3 - SSO will developed a Quality Assurance programme. | Ensure timely sharing of good quality information and co-ordination between Archdeacons and Diocese Safeguarding Team, including follow up of actions | In Progress | Recognising, Assessing and Managing Risk / Prevention | SMG / DSO / SSO & Archdeacons | 2026-06-01 | Define the process that the PA's need to request a Pre-visitation Safeguarding report once the appointment has been made from both Beth and Wendy (PI report to BC to be actioned)
Recommendation D4: Archdeacons should receive dedicated training and support regarding their functions as Core Group Chairs. Training should focus on facilitation skills for chairing these sensitive meetings and could be enhanced through the adoption of regional good practice workshops. Furthermore, to ensure impartiality, conflict of interest checks for chairs should be a standard practice. | Archdeacons to complete national training for SCMG. | Archdeacons trained, skilled and equipped to chair SCMG meetings | In Progress | Learning, Supervision & Support | Archdeacon of Durham | 2026-04-01 | Libby has completed the training and will cascade the training down to Katherine and Rick | Katherine will be trained by Libby in December. A date will be set for Rick to be trained when he is back from his sabbatical in January 2026.
Recommendation D5: Integrate robust methods to measure the impact of safeguarding practices across all relevant activities, including an enhanced programme of internal assurance audits. This enhanced programme could be significantly strengthened by developing a Parish Safeguarding Officer (PSO) skills database, enabling greater involvement of volunteers with relevant safeguarding skill sets in these crucial audits. Such measures will provide valuable data for continuous improvement and allow for a more effective evaluation of policy and practice. | SSO to organise skills database for PSOs to complete to identify areas of expertise across Diocese | Skills audit of PSOs to identify areas of expertise for sharing advice. Regular stakeholder surveys will obtain feedback as regards safeguarding practice of DST and provide appropriate assurances to DSAP regarding DST functions | Not yet started | Prevention | Diocesan Secretary / Business Service Manager | 2026-08-01
Recommendation D6: Establish a three-year meeting cycle for in-depth reviews of specific areas aligned with National Safeguarding Standards (NSS) and action plans. This cycle should be complemented by annual planning meetings with the Safeguarding Management Group (SMG) and other key stakeholders to ensure cohesive and complementary activities, thereby avoiding duplication of effort and enhancing the overall impact of safeguarding oversight. | On an annual basis an SMG meeting will be scheduled to identify the specific area for review in the coming 12 months and involve relevant stakeholders. | Regular review of all areas of safeguarding standards takes place | In Progress | Culture, Leadership & Capacity | DST and Archdeacons | 2026-02-01 |  | Meeting arranged between DST and 3 Archdeacons for 02.02.26
Recommendation D7: Conduct a comprehensive review of the functions of the SMG alongside those of the DSAP to ensure optimal strategic alignment and collaborative effectiveness in safeguarding oversight. | Align Terms of Reference of DSAP and SMG. | Effective and efficient operation of SMG and DSAP, safeguarding governance and oversight | Implemented | Culture, Leadership & Capacity | SMG / DSAP / SSO | 2026-06-01
Recommendation D8: Develop a written update proforma for Core DSAP members to complete before meetings. Core member status should be agreed by the Chair and include those with specific responsibilities or who represent agencies that offer valuable insights into current and developing safeguarding themes. Examples include the DSO/CSL/CSA, a Parish Safeguarding Officer (PSO) or Parish representative or an attendee from a charity or statutory partner. This proforma should concisely capture emerging safeguarding issues, the impact of their safeguarding practices during the last reporting period, and a dynamic question that changes after each meeting. This dynamic question is designed to address key issues such as the cost-of-living crisis, the implementation of the Jay Report, or any other relevant contemporary issue. The DSAP Chair should be given sufficient days to facilitate their outreach, especially to statutory agencies that are difficult to reach consistently. | Within the course of each DSAP meeting our external partners will be given the opportunity to share current and developing themes within their areas of expertise. The dynamic question will relate to the impact of key safeguarding issues on the Diocese | Improved understanding of contemporary safeguarding issues in geographical boundaries of Diocese relevant to our church and faith context. | Implemented | Culture Leadership & Capacity | DSAP Chair / DSO | 2026-01-01 | Meeting required with DSAP Chair to lead on this action. Discussion around recommendation in DSAP around how this will be addressed written proforma versus verbal report.
Recommendation D9: The Diocesan Safeguarding Officer (DSO) should formally record the examination of Blue Files upon both receipt and prior to dissemination, ensuring comprehensive record-keeping. | The DSO will use the proforma provided in the Maintenance of Clergy Blue Files Guidance to record all instances of when files have been reviewed. | Audit trail of who has accessed blue files established | Implemented | Prevention | DSO | 2025-09-01 | All blue files read by DSO will have the completed proforma placed on them
Recommendation D10: A strategic restructuring of the diocesan safeguarding arrangements should be undertaken to create a dedicated Safeguarding Directorate that is led by a professional Director of Safeguarding. This should also include the Cathedral’s safeguarding functions. Note: This recommendation should be read in conjunction with the Safeguarding Directorate section in the Independent Safeguarding Audits Annual Report (2024/2025).[1] | We will consider how to address this recommendation in light of further clarity from NST and the current work on future of safeguarding within national church context. The Diocese notes that INEQE's annual report refers to funding for this recommendation being provided by central church. See also D15. | Enhancement of the capacity of DST | Not yet started | Culture Leadership & Capacity | Diocesan Secretary | 2026-06-01
Recommendation D11: The DBF should immediately prioritise recruiting an additional full-time caseworker role, potentially as a job share, to increase team capacity and broaden the range of experience within the DST. | Scope out the role and to proceed to advert and recruitment | Increase capacity and diversify skill base of DST | In Progress | Culture Leadership & Capacity | DSO / HR | 2026-04-01
Recommendation D12: The DBF should develop a portfolio approach within the DST to enable more focused work on critical areas such as victim / survivor support, offender management, and training delivery. | Scope out in conjunction with Assistant DSA role (see D11). | Increase capacity and diversify skill base of DST | In Progress | Culture Leadership & Capacity | DSO / HR | 2026-04-01
Recommendation D13: A cost-benefit analysis of the current training provision should be conducted by the DBF. This analysis will determine the appropriateness of continuing with existing arrangements versus investing in an additional safeguarding professional and allocating a training budget for external provision when required. The primary objective of this review is to identify which model would most effectively enhance the DST’s overall capabilities and reach. | Undertake a cost benefit analysis to identify the training provision model that will most effectively enhance the overall capability and reach of the function. | Efficient and cost effective training delivery | Not yet started | Culture Leadership & Capacity | Diocesan Secretary | 2026-03-01 | Financial review of expenditure on cost of external trainers compared to employing a trainer within the Diocese.
Recommendation D14: The DBF should provide targeted training and upskilling for the Safeguarding Support Officer (SSO) to maximise their contribution to administering essential safeguarding support functions. These functions include Dashboard support, training evaluation, call filtering, and direct support to parishes. This enhancement would not only improve parish support but also facilitate the gathering of insights on safeguarding activities and efficiently filter non-safeguarding enquiries. | Targeted training and upskilling undertaken, identified through monthly supervision and annual performance review. | Real time support, progression and development of role holder, through internal and external opportunities. | In Progress | Learning, Supervision & Support | DSO / SSO | 2026-05-01
Recommendation D15: The DBF should embed the professional supervision of the Cathedral Safeguarding Advisor / Officer within the wider DST. This role should cultivate specialist knowledge in Cathedral safeguarding and serve as a contingency resource for the wider DST to address unforeseen operational demands. This arrangement should be reciprocal, offering contingency support within the Cathedral environment when required. | Recruitment of CSA to be professionally supervised by DSO | Development of working relationship between Diocese and Cathedral | In Progress | Culture Leadership & Capacity | Diocesan Secretary | 2026-03-01
Recommendation D16: In addition to the infrequent conversations outlined, the DBF should establish structured opportunities for informal safeguarding discussions and peer support. This could include regular ‘safeguarding coffee hours’ or ‘lunch and learn’ sessions for small groups of staff and / or promoting an internal online forum or chat group where staff can pose questions, share insights, and seek advice from colleagues and the DSO. The DBF should also ensure that line managers are encouraged and empowered to allocate time for these informal interactions within their teams. | Informal opportunities and peer support facilitated by DST | Improved developmental opportunities, supporting DBF staff and wider knowledge development | Not yet started | Learning, Supervision & Support | DSO | 2026-08-01
Recommendation D17: The DBF should adopt the use of an email marketing system for issuing and managing the safeguarding newsletter. | Email marketing system to be adopted for DST safeguarding newsletter in conjunction with Communications Team and monthly bulletin to be uploaded to website. | Support understanding of effectiveness of safeguarding communications | In Progress | Learning, Supervision & Support | SSO / Communications Team | 2026-02-01 | Monthly update to be renamed Newsletter
Recommendation D18: The DBF should conduct a review of its safeguarding webpages data to identify user behaviour patterns, popular content, and areas for improvement. The DBF should use the analysis of this data to inform and enhance the design, layout, user interface (UI), and user experience (UX) of the website. | An annual report on webpage engagement is presented to DSAP for consideration | Understanding of Diocesan safeguarding web page usage to inform future development of content and functions | Implemented | Prevention | SSO / Communications Team | 2025-10-01 |  | Annual report on safeguarding webpage engagement to be presented to DSAP
Recommendation D19: The DBF should develop and implement a structured communications plan for safeguarding messages across its digital channels. This plan should include a content calendar outlining timely, considered safeguarding messages for regular inclusion in email newsletters (e.g., a dedicated section or recurring feature) and scheduled posts on relevant social media platforms. Content should be varied, covering topics such as policy updates, training opportunities, real-life examples (anonymised), reminders of reporting mechanisms, and messages promoting a culture of vigilance and support. The DBF should assign responsibility for content creation, approval, and scheduling, ensuring all messages are consistent, accessible, and align with current safeguarding guidelines. Regular review of engagement metrics should inform future content strategy to maximise reach and impact. | Communications Team and DST will develop a communications plan covering safeguarding message across digital channels | Enhancement of Diocesan communications regarding safeguarding to maximise reach and impact | In Progress | Prevention | Director Communications / DSO / SSO | 2026-02-01
Recommendation D20: The DBF should undertake a review to map the types of activities involving children and young people that are taking place within parishes, what the focus of such activities are and to identify any aspects of good practice and / or potential gaps. | Strategic leads within DBF to review types of activities to identify best practice and gaps across Youth Voice and Participation, Networks for Staff and Volunteers, Youth and Children’s Mission Hubs, Diocesan and Regional Gatherings, Expansion of Chaplaincy, Young Adult Pilgrimage Pilot Project | Enhance understanding of current practice so that proactive advice can be provided | In Progress | Prevention | Growing Younger Strategic Lead | 2026-07-01
Recommendation D21: Further to reviewing existing practice, the DBF should consider implementing new and / or extended models for youth participation in consultation with parishes and its existing networks, including the Cathedral. | Strategic leads within DBF to review types of activities to identify best practice and gaps (see D21) | Improve youth participation and opportunities for youth voice to be heard | In Progress | Prevention | Growing Younger Strategic Lead | 2026-07-01 | Linked with D20
Recommendation D22: The DBF should include defined review dates for all risks described within its Risk Register(s). Risks should be reviewed on a quarterly basis or as a minimum, at a six-monthly basis, with any changes (and the rationale for these) being documented in relevant meeting minutes. | Six monthly reviews established, changes are documented along with the supporting rationale. | Risk register is up to date and facilitates enhanced risk management | Implemented | Recognising, Assessing and Managing Risk | Governance Support Manager | 2025-10-01 |  | Version control and review dates have been added to Risk Register. Rationale for any changes to be added from the next review period
Recommendation D23: The DBF should commission an external resource to comprehensively review, cleanse, and curate the inputting of existing data into the NSCMS. This activity should operate under terms of reference set by the DSO and adhere to the ‘Guiding Principles’ for the NSCMS. | External specialist commissioned to conduct a review and create an action plan | Improved consistency of NSCMS record keeping in compliance with national requirements | In Progress | Recognising, Assessing and Managing Risk | DSO | 2026-06-01 |  | Health check complete.
Recommendation D24: The DBF should implement a systematic process for the review and updating of all safeguarding risk assessments related to active Safety Plans. This process should include assessing new or evolving risks and revising control measures, ensuring continuous alignment with current good practice, integration of lessons learned from incidents (if any), and reflect a contemporary understanding of risks. These updates should adopt the current ‘Standard Risk Analysis and Risk Management’ format. | Risk assessments under the responsibility of the Diocese are reviewed at a minimum annually or whenever an incident occurs that requires re-assessment. All existing risk assessments to be transferred to new format at point of review. | Ensuring risk is managed appropriately for active Safety Plans | Implemented | Recognising, Assessing and Managing Risk | DSO | 2026-12-01
Recommendation D25: The DBF should proactively raise awareness of the dispute resolution pathway across the Diocese. | Complaints dispute resolution process published on website under the responsibility of the Diocese. Further steps to be considered on publication of national guidance around safeguarding complaints policy. | Ensuring complaints related to safeguarding are managed appropriately and effectively | Not yet started | Culture Leadership & Capacity | Business Service Manager (DSO for content) | 2026-03-01
Recommendation D26: The DBF should rapidly review the arrangements in place covering secure and accessible data management at a parish level. This should include a review of the guidance, equipment and technical solutions available to PSOs to undertake their safeguarding functions. | Best practice recommendations to be developed by DBF, in consultation with RSL/NST guidance. | Improved compliance with data management policies | Not yet started | Prevention | Business Service Manager | 2026-03-01
Recommendation D27: Notwithstanding the review of the arrangements in place, the DBF should advise all parishes that PSOs (and any other parish staff and volunteers handling sensitive data) should adopt a policy stipulating that confidential safeguarding records should not be stored on personal devices. | Best practice guidance to be provided in consultation with RSL/NST guidance. | Parish management of safeguarding records | Not yet started | Prevention | Business Service Manager | 2026-03-01
Recommendation D28: To mitigate risks associated with unforeseen circumstances such as the passing of a PSO, the DBF should develop and enact a comprehensive data succession plan. This plan should clearly outline: Designated Access: Who has authorised access to safeguarding records in the event of a PSO's incapacitation or departure (i.e. the DSO/DST) Secure Handovers: A formal process for the secure handover of all safeguarding data and associated access credentials when a PSO leaves their role. Emergency Access Procedures: Clearly defined procedures for gaining urgent access to vital safeguarding information in an emergency, including relevant technical support. | DBF to develop clear guidance on safeguarding records management for distribution to parishes | Improved efficiency of parish management of safeguarding records | Not yet started | Prevention | Business Service Manager / DSO | 2026-03-01
Recommendation D29: To ensure compliance and reinforce best practice, the DBF should: Conduct regular audits of data storage practices across all parishes to ensure adherence to the new protocols. Encourage ongoing training for all PSOs and relevant personnel on data protection, secure data storage, and the established data succession plan. This training should emphasise the critical importance of safeguarding sensitive information and the potential risks of non-compliance. | Data storage practice will be reviewed (see also D5, D26, D27, D28) by DBF. Training recommended via Parish Resources or alternatives where identified. | Best practice implemented within parishes for safeguarding data storage | Not yet started | Prevention | SSO / Business Service Manager | 2026-04-01
Recommendation D30: All members of the DST who may receive calls from distressed individuals should undergo training in: Trauma-Informed Practice: Understanding the impact of trauma on individuals and responding in a way that avoids re-traumatisation. Mental Health First Aid / Awareness: Basic understanding of common mental health conditions and how to support individuals experiencing a mental health crisis. Suicide Awareness and Intervention: Training on recognising signs of suicidal ideation and appropriate intervention strategies (e.g., signposting to crisis lines). Difficult Conversations and Conflict Resolution: Skills for navigating challenging conversations and managing potential conflict. | Appropriate training will be provided to DST colleagues. | Increase DST staff confidence and ability in dealing with calls from distressed individuals | Not yet started | Learning, Supervision & Support | DSO / Adviser in Pastoral Care, Counselling and Clergy Wellbeing | 2026-09-01
Recommendation D31: The DBF should further enhance its ‘Report Abuse’ webpage by incorporating direct signposts to local mental health services within the Durham region, e.g. the Mental Health Alliance. | Develop mental health information resources on 'Report Abuse' Diocesan webpage | Support information signposted and accessible for any victims and survivors needing to access mental health services | Implemented | Victims and Survivors | DSO / Communications Team | 2026-01-01
Recommendation D32: The DSO should schedule check-in points for victims and survivors, to create defined and diarised opportunities to engage with them. | DSO provides engagement opportunities for victims and survivors | Targeted support and appropriate service for victims and survivors | Implemented | Victims and Survivors | DSO | 2025-09-01 |  | Check in points scheduled with victims/survivors DSO working with
Recommendation D33: The DBF should strengthen its safeguarding telephone guidance for those receiving disclosures by incorporating a trauma-informed approach. This should include: · Providing a clear explanation of the importance of a trauma-informed approach. · Setting out how disclosures from potential victims and survivors may vary significantly based on their individual experiences. · Clear steps for assessing the caller's immediate safety and risk level and the actions to take in an emergency. · Guidance on using empathetic language, active listening techniques, and non-judgmental responses. · Strategies for calming distressed callers and managing potentially volatile conversations. · Guidance covering the local and national support services available to which distressed callers can be signposted. · Clear instructions on maintaining confidentiality while adhering to safeguarding and data protection regulations. · Guidance on maintaining professional boundaries and managing personal emotional impact. · Protocols for concluding calls in a way that leaves the caller feeling supported and informed of next steps. · Guidance on the support available via debriefs / supervision with managers, peer support mechanisms, and access to Employee Assistance. | Additional guidance will be provided to staff, based on trauma informed approach | Upskilling of staff who may potentially deal with receiving disclosures | Not yet started | Learning, Supervision & Support | DSO | 2026-02-01 | Specific training session for call handlers
Recommendation D34: The DBF should partner with the Cathedral to host Diocese-wide listening events, expanding the platform to hear from diverse voices that can help to shape local safeguarding strategy and practice. Such initiatives require careful execution, ensuring active listening, appropriate responses, and effective awareness-raising. | DBF will work with Cathedral to plan Diocese wide 'listening' events | Increased opportunity for diversity of voices to be heard | Not yet started | Victims and Survivors | DSO | 2026-09-01 | Subject to CSA/CSO appointment.
Recommendation D35: The DBF should explore a proportionate, Diocese-wide evaluation process for safeguarding training that evidences impact and is focused on confidence, behavioural change, and culture. | DBF will implement an appropriate evaluation mechanism for safeguarding training delivery | Quality assurance of impact of training and insight into developmental needs | Not yet started | Learning, Supervision & Support | DSO | 2026-06-01
Recommendation D36: The DBF should enhance support to PSOs by expanding accessible peer learning opportunities and introducing targeted micro-training or drop-in forums, particularly in high-need or low-capacity parishes. | DBF commissions additional training from external safeguarding training provider and provides quarterly PSO in person meetings facilitated by DST | Enhanced support for PSOs, via learning opportunities and networking offerings | Implemented | Learning, Supervision & Support | DSO | 2025-09-01 |  | Trauma informed response to disclosure training provided in 2025. Six masterclasses on safeguarding subjects have been commissioned.
KEY:
DBF - Diocesan Board of Finance
DSAP - Diocesan Safeguarding Advisory Panel
DSO - Diocesan Safeguarding Officer
SMG- Safeguarding Management Group
SSO - Safeguarding Support Officer
RSL - Regional Safeguarding Lead
NST - National Safeguarding Team
PSO- Parish Safeguarding Officer
DST - Diocesan Safeguarding Team
CSA- Cathedral Safeguarding Adviser